## Overview
Section | Value | Unit
Implementation - Total hours | 138 | h
Implementation - Total mandays | 17.25 | days
Implementation - Total cost | 49562.5 | CZK
Hardware price | 907 | CZK
Non-impl. Overhead - cost | 60487.5 | CZK
Annual operating costs | 37500 | CZK
Hourly rate (with VAT) | 403.75 | CZK
5-year total price | 260957 | CZK

## Implementation Tasks
Category | Task | Hours | Cost (CZK) | Mandays
Hardware | Install Pi into the case | 2 | 750 | 0.25
8
Hardware | Install sensors | 2 | 750 | 0.25
Hardware | Install bluetooth interface | 2 | 750 | 0.25
Hardware | OS installation | 4 | 1500 | 0.5
Development | Environment set up | 20 | 7500 | 2.5
Development | Design case | 10 | 3750 | 1.25
Software Backend | App skeleton | 5 | 1875 | 0.625
Software Backend | App bluetooth | 5 | 1875 | 0.625
Software Backend | Data retrieval | 2 | 750 | 0.25
Software Backend | Decryption | 2 | 750 | 0.25
Software Backend | Data transformation | 2 | 750 | 0.25
Software Backend | Data collection | 5 | 1875 | 0.625
Software Backend | Encryption | 2 | 750 | 0.25
Software Backend | Data transmission | 10 | 3750 | 1.25
Software Frontend | "Advanced" menu | 15 | 5625 | 1.875
Software Frontend | "Simple" menu | 10 | 3750 | 1.25
Software Frontend | Settings menu | 5 | 1875 | 0.625
Testing | Functional test | 10 | 3125 | 1.25
Testing | Non-functional tests | 10 | 3125 | 1.25
[5 empty] | testing | 65 |  | 22.8873
Testing | Scenario tests | 15 | 4687.5 | 1.875 | SW | 153 |  | 53.8732
[5 empty] | admin | 66 |  | 23.2394
[6 empty] | 284 |  | 2.84 | 100
-

## Non-Implementation Tasks
Category | Task | Hours | Cost (CZK) | Mandays
Administration | Team meetings | 30 | 12112.5 | 3.75
Administration | Client meetings | 6 | 3375 | 0.75
Administration | SRS | 40 | 22500 | 5
Administration | Bussiness plan | 10 | 5625 | 1.25
Documentation | User manual | 10 | 5625 | 1.25
Documentation | Troubleshooting guides | 10 | 5625 | 1.25
Documentation | Technical documentation | 10 | 5625 | 1.25

## Hardware Price
Component | Unit price + VAT | Qty | Total | URL | Date of price check
Raspberry Pi Zero 2 W | 419 | 1 | 419 | https://rpishop.cz/raspberry-pi-zero/4311-raspberry-pi-zero-2-w.html | 23.3.2026
Waveshare Laser Sensor | 230 | 1 | 230 | https://www.waveshare.com/laser-sensor.htm | 23.3.2026
Ultrasound sensor HC-SR04 | 39 | 2 | 78 | https://rpishop.cz/vzdalenost/815-ultrazvukovy-senzor-hc-sr04.html | 23.3.2026
Time-of-flight sensor VL53LDK | 90 | 2 | 180 | https://allegro.cz/produkt/czujnik-odlegosci-vl53l0x-49792d4c-b92b-4d7e-b4a2-6177db786a88?offerId=9363139945&utm_feed=712e6653-4749-4512-b084-b6e297fc9e0b&utm_source=google&utm_medium=cpc&utm_campaign=CZ%3EElectro%3EHome-electro%3E3P%3EPMAX&ev_campaign_id=20035822444&gad | 23.3.2026

## Staffing & Resources
Role | Salary / month | Utilisation | Hrly cost
SW Engineer Junior | 60000 | 54% | 375
Tester | 50000 | 23% | 312.5
Team leader | 90000 | 23% | 562.5

## Yearly Payments
Cost Item | Hours annualy | Staff member | Annual Cost
Maintanence | 100 | SW Engineer Junior | 37500